## Scope
CIRM- Action Plan
| Tasks | Dependencies | Estimate
A | Automation Test Suite Development
1 | Requirement Gathering
2 | Create Understanding document | A1
3 | Validate by the client | A2
4 | Create Test cases | A3
5 | Testcase validate by client | A4
6 | Bug Identification | A5
7 | Prioritize the bugs | A6
8 | Client validate the bugs | A7
9 | Bugs fixes is completed by client, then do the retest | A8
10 | Regression testing | A9
11 | Automation Environment setup | A10
12 | Tool Chosen for the application | A11
13 | Framework creation | A12
14 | Created the Automation Test script with the validated testcases | A13
15 | Validate the test script with the excelencia team | A14
16 | Validate the test script with client | A15
17 | Report Generation | A16
18 | Setup the environment to the client machine | A17
19 | Send the code and run it in client machine | A18
20 | Test closing report | A19

## Tools Selection Creteria
S.No | Parameters | Priority | Selenium(Excelencia Framework) |  | Cypress(Excelencia Framework) |  | Remarks
|  |  | Yes | No | Yes | No
1 | Ease of use | Medium
2 | Suitable to CIRM | High
3 | Easy to maintain | High
4 | write scripts | Medium
5 | Browser Support | Medium
6 | Built in Server Mocking | Medium
7 | Easy to execute | Medium
8 | Easy Test syntax | Medium
9 | Easy to Debug | Medium
10 | Test speed and performance | High
11 | Functional Coverage | High
12 | Code coverage | High
13 | Community/Ecosystem | Medium
14 | Easy to reusable | High
15 | CI/CD pipe line | High
16 | DataDriven approach | Medium
17 | Report generations | Medium
18 | Document uploads | Medium
19 | Alert Handling | Medium
20 | Synchronizations | High

## Sheet1
S.no | Limitations of Cypress
1 | Only Javascript support for test case creation/execution
2 | There is no multi-language support like Selenium
3 | Driving two browsers at once is not possible
4 | While Selenium allows screen capture, it does not allow for the testing of images, videos, or audio
5 | Limited support for mobile testing
6 | No multiple tabs support
7 | Since it runs directly on the browser, running e2e tests combining multiple platforms is not possible
8 | Limited support for iFrames

## Project Plan
CIRM- Project Plan
| Tasks | Dependencies | Resources | Estimate
A | Automation Test Suite Development
Discovery Phase
I | Requirement Gathering
1 | Understanding Critical (Application) Workflows
2 | GMS Application Testing Approach Plan
3 | Test Strategy Creation
4 | Test Case Creation
II | SDLC Understanding
1 | Development Environment Understanding
2 | Validate Existing Code (Ruby)
III | Testing Strategy (Process Understanding)
1 | Unit Testing Process
2 | Test Case Creation Process
1V | Decision making Creteria
1 | User Document creation
2 | QA Process document creation
3 | Environment setup for Automation
4 | Decision Making for EDUC1 and CLIN1 Application with multiple tools
V | Recommendation
1 | QA Process and Automation Test strategy
2 | Suitable Automation tool and framework
3 | Distinct workflows Identification
4 | Virtual Machines for the environment setup
Implementation Phase
I | Environment Setup
1 | Environment setup for the recommended tool and framework
2 | Automation Test suite development plan creation
3 | Automation Test script creation for distinct workflows
II | Environment Setup for CIRM
1 | Environment setup for Virtual machines
2 | Knowledge Transfer for Automation tools ans scripts
3 | Handover the test scripts
4 | Verify the working statusof Test scripts
5 | Test closure report creation