## Sheet2 (hidden)
Month | Days
January | 23
February | 20
March | 21
April | 22
May | 23
June | 21
July | 23
August | 22
September | 21
October | 23
November | 21
December | 22

## Ancy
Employee Name |  | J. Xavi Ahisha Ancy
Name of the Project |  | CIRM-GMS Application
Name of the Project Manager |  | Rajesh Sampath
Month |  | September
Sno | Task Name | Task Description | % of completion | Planned Start Date | Planned End Date | Planned Duration | Actual Start Date | Actual End Date | Actual Duration | Schedule Variance | Planned Effort (in hours) | Actual Effort (in hours) | Effort Variance | Status | Remarks
1 | Progress reporting for CLIN1 | Document - Requirements | 100% | 2023-08-21 | 2023-08-21 | 1 | 2023-09-01 | 2023-09-01 | 1 | 0% | 8 | 8 | 0% | Completed
2 |  | Automation Script Development | 100% | 2023-08-22 | 2023-08-31 | 8 | 2023-09-04 | 2023-09-07 | 4 | -50% | 64 | 32 | -50% | Completed
3 |  | Script Checkin & Validation (local) | 100% | 2023-09-01 | 2023-09-01 | 1 | 2023-09-08 | 2023-09-08 | 1 | 0% | 8 | 8 | 0% | Completed
4 | Progress reporting for EDUC4 | Document - Requirements | 100% | 2023-09-04 | 2023-09-05 | 2 | 2023-09-11 | 2023-09-11 | 1 | -50% | 16 | 8 | -50% | Completed
5 |  | Automation Script Development | 100% | 2023-09-05 | 2023-09-14 | 8 | 2023-09-12 | 2023-09-21 | 6 | -25% | 64 | 48 | -25% | Completed
6 |  | Script Checkin & Validation (local) | 100% | 2023-09-15 | 2023-09-15 | 1 | 2023-09-22 | 2023-09-22 | 1 | 0% | 8 | 8 | 0% | Completed
7 |  | Total Script validation | 100% | 2023-09-25 | 2023-09-29 | 5 | 2023-09-25 | 2023-09-29 | 5 | 0% | 40 | 40 | 0% | Completed
[6 empty] | 0 |  |  | 0 | 0% |  |  | 0%
[6 empty] | 0 |  |  | 0 | 0% |  |  | 0%
[6 empty] | 0 |  |  | 0 | 0% |  |  | 0%
[6 empty] | 0 |  |  | 0 | 0% |  |  | 0%
[6 empty] | 0 |  |  | 0 | 0% |  |  | 0%
Insert Line Before
[11 empty] | 208 | 152
Month Of Reporting |  | September
No of Days |  | 21
Available Effort |  | 168
Planned Effort |  | 208
Actual Effort |  | 152
Planned Utilization (%) |  | 123.8%
Actual Utilzation (%) |  | 90.48%
Effort Variance |  | -26.92%
Schedule Variance |  | -10.42%
Efficiency |  | 100%
Formulas:
Planned Duration = NETWORKDAYS([Planned Start Date],[Planned End Date])
Actual Duration = NETWORKDAYS([Actual Start Date],[Actual End Date])

## Summary
Month Of Reporting |  | September
No of Days |  | 21
Available Effort |  | 168
Planned Effort |  | 208
Actual Effort |  | 152
Planned Utilization (%) |  | 123.8%
Actual Utilzation (%) |  | 90.48%
Effort Variance |  | -26.92%
Schedule Variance |  | -10.42%
Efficiency |  | 100%
Ancy
Planned Utilization | 123.8%
Actual Utilzation | 90.48%
Average Effort Variance | -26.92%
Average Schedule Variance | -10.42%
Average Efficiency | 100%