## gms qa testing
GMS QA Testing
Discovery, Documentation & Planning
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Module Requirements Collection |  | Xavi Ahisha Ancy J | Done | 2023-06-19 | 2023-07-14 | 100% |  | 80 | T1,T2
Requirements Documentation |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-07-14 | 100% |  | 80 | T1,T2 | Module Requirements Collection
|  |  |  | 2023-06-19 to 2023-07-04 | 2023-07-14 | 100% |  | 160
CLIN1
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document CLIN1 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-06-13 | 100% |  | 12 | T1 | Module Requirements Collection
CLIN1 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-06-14 | 100% |  | 24 | T1 | Document CLIN1 Requirements
CLIN1 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-06-16 | 100% |  | 4 | T2 | CLIN1 Automation Script Development
CLIN1 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-16 | 100% |  |  | C1 | CLIN1 Script Checkin & Validation (local)
CLIN1 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | CLIN1 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | CLIN1 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-06-13 to 2023-09-13 | 100% |  | 40
CLIN2
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document CLIN2 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-07-19 | 100% |  | 12 | T2 | Module Requirements Collection
CLIN2 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-07-19 | 100% |  | 24 | T2 | Document CLIN2 Requirements
CLIN2 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-07-19 | 100% |  | 4 | T1 | CLIN2 Automation Script Development
CLIN2 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | CLIN2 Script Checkin & Validation (local)
CLIN2 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | CLIN2 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | CLIN2 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-07-13 to 2023-09-13 | 100% |  | 40
TRAN1
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document TRAN1 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-07-20 | 100% |  | 12 | T1 | Module Requirements Collection
TRAN1 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-21 | 2023-07-21 | 100% |  | 24 | T1 | Document TRAN1 Requirements
TRAN1 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-22 | 2023-07-24 | 100% |  | 4 | T2 | TRAN1 Automation Script Development
TRAN1 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-23 | 2023-07-13 | 100% |  |  | C1 | TRAN1 Script Checkin & Validation (local)
TRAN1 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-24 | 2023-09-13 | 100% |  |  | C1 | TRAN1 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-25 | 2023-09-13 | 100% |  |  | C1 | TRAN1 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-25 | 2023-07-13 to 2023-09-13 | 100% |  | 40
TRAN2
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document TRAN2 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-06-20 | 100% |  | 12 | T2 | Module Requirements Collection
TRAN2 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-06-21 | 100% |  | 24 | T2 | Document TRAN2 Requirements
TRAN2 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-06-23 | 100% |  | 4 | T1 | TRAN2 Automation Script Development
TRAN2 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | TRAN2 Script Checkin & Validation (local)
TRAN2 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | TRAN2 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | TRAN2 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-06-20 to 2023-09-13 | 100% |  | 40
TRAN3
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document TRAN3 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-06-20 | 100% |  | 12 | T1 | Module Requirements Collection
TRAN3 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-06-21 | 100% |  | 24 | T2 | Document TRAN3 Requirements
TRAN3 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-06-23 | 100% |  | 4 | T1 | TRAN3 Automation Script Development
TRAN3 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-09-12 | 100% |  |  | C1 | TRAN3 Script Checkin & Validation (local)
TRAN3 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-12 | 100% |  |  | C1 | TRAN3 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | TRAN3 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-06-20 to 2023-09-13 | 100% |  | 40
TRAN4
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document TRAN4 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-06-27 | 100% |  | 12 | T1 | Module Requirements Collection
TRAN4 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-06-28 | 100% |  | 24 | T1 | Document TRAN4 Requirements
TRAN4 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-06-30 | 100% |  | 4 | T2 | TRAN4 Automation Script Development
TRAN4 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-09-12 | 100% |  |  | C1 | TRAN4 Script Checkin & Validation (local)
TRAN4 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-12 | 100% |  |  | C1 | TRAN4 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | TRAN4 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-06-27 to 2023-09-13 | 100% |  | 40
DISC0
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document DISC0 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-06-27 | 100% |  | 12 | T2 | Module Requirements Collection
DISC0Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-06-28 | 100% |  | 24 | T2 | Document DISC0 Requirements
DISC0 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-06-30 | 100% |  | 4 | T1 | DISC0Automation Script Development
DISC0 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-09-01 | 100% |  |  | C1 | DISC0 Script Checkin & Validation (local)
DISC0 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-12 | 100% |  |  | C1 | DISC0 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-06-27 to 2023-09-13 | 100% |  | 40
DISC2
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document DISC2 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-06-27 | 100% |  | 12 | T1 | Module Requirements Collection
DISC2 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-06-28 | 100% |  | 24 | T2 | Document DISC2 Requirements
DISC2 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-06-30 | 100% |  | 4 | T1 | DISC2 Automation Script Development
DISC2 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | DISC2 Script Checkin & Validation (local)
DISC2 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | DISC2 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | DISC2 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-06-27 to 2023-09-13 | 100% |  | 40
EDUC1.10
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document EDUC1.10 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-06-13 | 100% |  | 12 | T1 | Module Requirements Collection
EDUC1.10 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-06-14 | 100% |  | 24 | T2 | Document EDUC1.10 Requirements
EDUC1.10 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-06-16 | 100% |  | 4 | T1 | EDUC1.10 Automation Script Development
EDUC1.10 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | EDUC1.10 Script Checkin & Validation (local)
EDUC1.10 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-12 | 100% |  |  | C1 | EDUC1.10 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | EDUC1.10 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-06-13 to 2023-09-13 | 100% |  | 40
EDUC2
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document EDUC2 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-07-04 | 100% |  | 12 | T1 | Module Requirements Collection
EDUC2 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-07-05 | 100% |  | 24 | T1 | Document EDUC2 Requirements
EDUC2 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-07-07 | 100% |  | 4 | T2 | EDUC2 Automation Script Development
EDUC2 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | EDUC2 Script Checkin & Validation (local)
EDUC2 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | EDUC2 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | EDUC2 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-07-04 to 2023-09-13 | 100% |  | 40
EDUC3
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document EDUC3 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-07-04 | 100% |  | 12 | T2 | Module Requirements Collection
EDUC3 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-07-05 | 100% |  | 24 | T2 | Document EDUC3 Requirements
EDUC3 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-07-07 | 100% |  | 4 | T1 | EDUC3 Automation Script Development
EDUC3 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | EDUC3 Script Checkin & Validation (local)
EDUC3 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | EDUC3 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | EDUC3 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-07-04 to 2023-09-13 | 100% |  | 40
EDUC4
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document EDUC4 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-04 | 2023-07-04 | 100% |  | 12 | T1 | Module Requirements Collection
EDUC4 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-05 | 2023-07-05 | 100% |  | 24 | T2 | Document EDUC4 Requirements
EDUC4 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-06 | 2023-07-07 | 100% |  | 4 | T1 | EDUC4 Automation Script Development
EDUC4 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | EDUC4 Script Checkin & Validation (local)
EDUC4 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | EDUC4 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | EDUC4 Script Checkin & Validation (staging)
|  |  |  | 2023-07-04 to 2023-07-20 | 2023-07-04 to 2023-09-13 | 100% |  | 40
EDUC5
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document EDUC5 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-07 | 2023-07-07 | 100% |  | 12 | T1 | Module Requirements Collection
EDUC5 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-08 | 2023-07-13 | 100% |  | 24 | T1 | Document EDUC5 Requirements
EDUC5 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-12 | 2023-07-13 | 100% |  | 4 | T2 | EDUC5 Automation Script Development
EDUC5 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | EDUC5 Script Checkin & Validation (local)
EDUC5 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | EDUC5 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | EDUC5 Script Checkin & Validation (staging)
|  |  |  | 2023-07-07 to 2023-07-20 | 2023-07-07 to 2023-09-13 | 100% |  | 40
INFR4
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document INFR4 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-07 | 2023-07-07 | 100% |  | 12 | T2 | Module Requirements Collection
INFR4 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-08 | 2023-07-13 | 100% |  | 24 | T2 | Document INFR4 Requirements
INFR4 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-12 | 2023-07-13 | 100% |  | 4 | T1 | INFR4 Automation Script Development
INFR4 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | INFR4 Script Checkin & Validation (local)
INFR4 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | INFR4 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-15 | 100% |  |  | C1 | INFR4 Script Checkin & Validation (staging)
|  |  |  | 2023-07-07 to 2023-07-20 | 2023-07-07 to 2023-09-15 | 100% |  | 40
INFR5
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document INFR5 Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-07 | 2023-07-07 | 100% |  | 12 | T1 | Module Requirements Collection
INFR5 Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-08 | 2023-07-13 | 100% |  | 24 | T2 | Document INFR5 Requirements
INFR5 Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-12 | 2023-07-13 | 100% |  | 4 | T1 | INFR5 Automation Script Development
INFR5 Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-13 | 2023-07-13 | 100% |  |  | C1 | INFR5 Script Checkin & Validation (local)
INFR5 Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-18 | 2023-09-13 | 100% |  |  | C1 | INFR5 Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-20 | 2023-09-13 | 100% |  |  | C1 | INFR5 Script Checkin & Validation (staging)
|  |  |  | 2023-07-07 to 2023-07-20 | 2023-07-07 to 2023-09-13 | 100% |  | 40
Review Modules for CLIN
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document - Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-17 | 2023-07-18 | 100% |  | 12 | T1 | Module Requirements Collection
Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-18 | 2023-07-20 | 100% |  | 24 | T1,T2 | Document - Requirements
Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-21 | 2023-07-21 | 100% |  | 4 | T2 | Automation Script Development
Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-31 | 2023-07-31 | 100% |  |  | C1 | Script Checkin & Validation (local)
Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-01 | 2023-09-13 | 100% |  |  | C1 | Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-02 | 2023-09-13 | 100% |  |  | C1 | Script Checkin & Validation (staging)
|  |  |  | 2023-07-17 to 2023-08-02 | 2023-07-18 to 2023-09-13 | 100% |  | 40
Review Modules for DISC
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document - Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-24 | 2023-07-25 | 100% |  | 12 | T2 | Module Requirements Collection
Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-07-25 | 2023-07-27 | 100% |  | 24 | T1,T2 | Document - Requirements
Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-07-28 | 2023-07-28 | 100% |  | 4 | T1 | Automation Script Development
Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-07-31 | 2023-07-31 | 100% |  |  | C1 | Script Checkin & Validation (local)
Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-01 | 2023-09-13 | 100% |  |  | C1 | Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-03 | 2023-09-13 | 100% |  |  | C1 | Script Checkin & Validation (staging)
|  |  |  | 2023-07-24 to 2023-08-03 | 2023-07-25 to 2023-09-13 | 100% |  | 40
Award Creation and Closeout for CLIN1
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document - Requirements |  | Xavi Ahisha Ancy J | Done | 2023-07-31 | 2023-08-01 | 100% |  | 12 | T1 | Module Requirements Collection
Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-08-01 | 2023-08-18 | 100% |  | 40 | T1,T2 | Document - Requirements
Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-08-02 | 2023-08-08 | 100% |  | 4 | T2 | Automation Script Development
Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-21 | 2023-08-21 | 100% |  |  | C1 | Script Checkin & Validation (local)
Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-22 | 2023-09-14 | 100% |  |  | C1 | Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-24 | 2023-09-15 | 100% |  |  | C1 | Script Checkin & Validation (staging)
|  |  |  | 2023-07-31 to 2023-08-24 | 2023-08-01 to 2023-09-15 | 100% |  | 56
Award Creation and PFAR for EDUC4
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document - Requirements |  | Xavi Ahisha Ancy J | Done | 2023-08-09 | 2023-08-10 | 100% |  | 12 | T2 | Module Requirements Collection
Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-08-10 | 2023-08-17 | 100% |  | 40 | T1,T2 | Document - Requirements
Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-08-18 | 2023-08-18 | 100% |  | 4 | T1 | Automation Script Development
Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-21 | 2023-08-21 | 100% |  |  | C1 | Script Checkin & Validation (local)
Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-22 | 2023-08-23 | 100% |  |  | C1 | Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-08-24 | 2023-09-15 | 100% |  |  | C1 | Script Checkin & Validation (staging)
|  |  |  | 2023-08-09 to 2023-08-24 | 2023-08-10 to 2023-09-15 | 100% |  | 56
Progress reporting and Checklist for CLIN1
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document - Requirements |  | Xavi Ahisha Ancy J | Done | 2023-08-21 | 2023-09-08 | 100% |  | 12 | T1 | Module Requirements Collection
Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-08-22 | 2023-09-08 | 100% |  | 64 | T1,T2 | Document - Requirements
Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-09-01 | 2023-09-08 | 100% |  | 4 | T2 | Automation Script Development
Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-09-18 | 2023-09-18 | 100% |  |  | C1 | Script Checkin & Validation (local)
Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-09-19 | 2023-09-13 | 100% |  |  | C1 | Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-09-21 | 2023-09-13 | 100% |  |  | C1 | Script Checkin & Validation (staging)
|  |  |  | 2023-08-21 to 2023-09-21 | 2023-09-08 to 2023-09-18 | 100% |  | 80
Progress reporting and Checklist for EDUC4
Name | Subitems | Person | Status | Start Date | End Date | Progress | monday Doc | Duration | Resources | Dependent On | Notes
Document - Requirements |  | Xavi Ahisha Ancy J | Done | 2023-09-04 | 2023-09-08 | 100% |  | 12 | T2 | Module Requirements Collection
Automation Script Development |  | Xavi Ahisha Ancy J | Done | 2023-09-05 | 2023-09-14 | 100% |  | 64 | T1,T2 | Document - Requirements
Script Checkin & Validation (local) |  | Xavi Ahisha Ancy J | Done | 2023-09-15 | 2023-09-14 | 100% |  | 4 | T1 | Automation Script Development
Script Release |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-09-18 | 2023-09-14 | 100% |  |  | C1 | Script Checkin & Validation (local)
Script Checkin & Validation (staging) |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-09-19 | 2023-09-14 | 100% |  |  | C1 | Script Release
Sign-Off |  | Douglas Guillen, Alan Kropp, Mason Saia, venkat Kagithala | Done | 2023-09-21 | 2023-09-15 | 100% |  |  | C1 | Script Checkin & Validation (staging)
|  |  |  | 2023-09-04 to 2023-09-21 | 2023-09-08 to 2023-09-15 | 100% |  | 80