## TM
RTMID | Task Description | Status | Expected Date | Actual Date | Test Case ID | Mantis ID
RTMSO#000 | UI Designs |  | Fri 7/22/16
RTMSO#001 | Splash screen for the mobile app |  | #REF! | #REF! | TC001
PROJECTS
RTMSO#002 | Create project via pop-up |  | #REF! |  | TC002-TC016
RTMSO#003 | Edit/Delete projects |  | #REF! |  | TC020-TC032
SEQUENCE
RTMSO#004 | Create/Edit sequence via pop-up |  | #REF! |  | TC061-TC073, TC099-TC103
RTMSO#005 | Drag and re-order sequence |  | #REF! |  | TC074, TC075
SEGMENT
RTMSO#006 | Create segment via pop-up |  | #REF! |  | TC048-TC060
RTMSO#007 | Edit / filter segment |  | #REF! |  | TC079-TC098
INDEX CARD
RTMSO#008 | Create index card / edit |  | #REF! |  | TC104-TC131
RTMSO#009 | Numbering preferences (2) index card |  | #REF!
RTMSO#010 | Dupe / delete index card |  | #REF! |  | TC131-TC135
UI Design- Expanded/Collapsed outline
RTMSO#011 | Landing page (sequence cards in top view) |  | #REF! |  | TC033-TC047, TC076-TC078
RTMSO#012 | Project outline page #1 (sequence & expanded index in top view) |  | #REF!
RTMSO#013 | Project outline page #2 (sequence & collapsed index in top view) |  | #REF!
RTMSO#014 | Display & edit sequence cards |  | #REF!
RTMSO#015 | Display segment cards |  | #REF!
RTMSO#016 | Display index cards |  | #REF!
RTMSO#017 | Size slider |  | #REF!
EXPORT
RTMSO#018 | Export to Text |  | #REF! |  | TC136-TC147
RTMSO#019 | Export to StoryO desktop |  | #REF!
RTMSO#020 | IMPORT from StoryO |  | #REF! |  | TC017-TC019